Using Microsoft Project do the following project schedule and then answer the questions that follow

- Create a project for developing a website with the following phases

  - Requirements

  - Analysis

  - Development

  - Testing

- Onboard your team

  - Messi (BA) Rate 100 $/hr

  - Rocky (Dev) Rate 125 $/hr  + Overtime rate 150$/hr

  - Kate (QA) Rate 80 $/hr

- Create two tasks under each phase and assign resources appropriately

  - For requirements

    - BRD Authoring (Messi – 100%) – 2 weeks

    - BRD Review (Messi – 50%, Rocky 50%) – 3 days

  - Analysis

    - FSD authoring (Messi – 100%) – 2 weeks

    - FSD Review (Messi – 50%, Rocky 50%) – 5 days

  - Development

    - Developing the website (Rocky 100%, Messi 25%) – 5 weeks

    - Unit Testing (Rocky 100%, Messi 25%) – 2 weeks

  - Testing

    - Test case authoring (Kate 100%) – 1 week

    - Test case execution (Kate 75%, Messi 25%, Rocky 75%) – 4 weeks

- Dependencies

  - BRD Review can start half way when Authoring is done

  - FSD Authoring can start in paralles to BRD review

  - Development has to start after analysis is completed

  - Test case authoring can start after BRD review is completed

  - Test case execution has to start after unit testing is completed

Demonstrate the following

- Develop the project schedule showing dependencies

- Gantt Chart

- Critical path

- Resource Leveling

Before Leveling

After Leveling

- Setting project baseline

- Earned value cost indicators

- Earned value schedule indicators

- Showing slack in the Gantt chart

- Add a milestone

- Demonstrate a custom report to show resource usage (optional)

- Timeline to copy into a presentation

Start
Tue 12/1/15

Finish
Mon 3/21/16

December 1

January 1

February 1

March 1

Today

- Calculate Budget